## Bug Report Template
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)

## User Registration
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)
1 | Open | Mahfouz Sherif | TC-UR-004 | 1. Go to Signup page 2. Enter numeric name (e.g., “12345”) 3. Click “Signup” | System should display “Invalid name” error | Page proceeds to “Enter Account Information” successfully | Medium | Medium | link
2 | Open | Mahfouz Sherif | TC-UR-005 | 1. Go to Signup page 2. Enter special characters in Name (e.g., “@@@Mahfouz###”) 3. Click “Signup” | System should display “Invalid name” error | Page proceeds to “Enter Account Information” successfully | Medium | Medium | link
3 | Open | Mahfouz Sherif | TC-UR-007 | 1. Go to Signup page 2. Enter invalid email (e.g., “mahfouz@mail”) 3. Click “Signup” | System should display “Invalid email format” error | Page proceeds to “Enter Account Information” successfully | High | High | link
4 | Open | Mahfouz Sherif | TC-UR-012 | 1. Go to Enter Account Information page 2. Enter short password (e.g., “123”) 3. Click “Create Account” | System should display “Password too short” error | Account successfully created and “Account Created!” message displayed | High | High | link
5 | Open | Mahfouz Sherif | TC-UR-014 | 1. Go to Enter Account Information page 2. Enter numeric first name (e.g., “12345”) 3. Click “Create Account” | System should display “Invalid first name” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link
6 | Open | Mahfouz Sherif | TC-UR-015 | 1. Go to Enter Account Information page 2. Enter special characters in First Name (e.g., “@@@Mahfouz###”) 3. Click “Create Account” | System should display “Invalid first name” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link
7 | Open | Mahfouz Sherif | TC-UR-017 | 1. Go to Enter Account Information page 2. Enter numeric last name (e.g., “12345”) 3. Click “Create Account” | System should display “Invalid last name” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link
8 | Open | Mahfouz Sherif | TC-UR-018 | 1. Go to Enter Account Information page 2. Enter special characters in Last Name (e.g., “@@@Mahfouz###”) 3. Click “Create Account” | System should display “Invalid last name” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link
9 | Open | Mahfouz Sherif | TC-UR-024 | 1. Go to Enter Account Information page 2. Enter letters or symbols in Zipcode (e.g., “abcd”, “123@”) 3. Click “Create Account” | System should display “Invalid Zipcode” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link
10 | Open | Mahfouz Sherif | TC-UR-026 | 1. Go to Enter Account Information page 2. Enter non-numeric Mobile Number (e.g., “abcde”, “12@#”) 3. Click “Create Account” | System should display “Invalid mobile number” error | Account successfully created and “Account Created!” message displayed | Medium | Medium | link

## Product Search
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)
PS_BUG_01 | Open | ZIAD BADR | TC-PS-01 | 1. Enter 'T-shirt' in search bar 2. Click Search | All T-shirts should be listed | Only partial results displayed | Medium | High
PS_BUG_02 | Open | ZIAD BADR | TC-PS-02 | 1. Enter 'Laptop' in search bar 2. Click Search | No products found' message displayed | No message shown, blank area appears | Low | Medium
PS_BUG_03 | Open | ZIAD BADR | TC-PS-03 | 1. Enter 't-shirt' in lowercase 2. Click Search | Same results as 'T-shirt' | No results for lowercase search | High | High
PS_BUG_04 | Open | ZIAD BADR | TC-PS-04 | 1. Enter '@#$%^' in search bar 2. Click Search | Display 'No products found' | Page crashes | High | High
PS_BUG_05 | Open | ZIAD BADR | TC-PS-05 | 1. Leave search empty 2. Click Search | Show all products or warning message | Blank page appears | Low | Low

## Account Deletion
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)
AD03-CancelDeletion-MissingOption | Open | Hagar Tamer Mohamed | AD03 | 1. Click "Delete Account" 2. On confirmation prompt, attempt to click "Cancel" | A "Cancel" option should be available and account remains active | No "Cancel" option is available; account is deleted immediately. | High | High | https://drive.google.com/file/d/1JsvxLQjbliiIyAkAw17YxgrPMlHKWmLZ/view?usp=sharing

## Checkout & Payment
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)
1 | Open | Rahma Sayed | CP06 | 1. Go to Checkout → Payment page. 2. Enter Name on card: mohamed123 3. Enter valid 16-digit card number, CVC, and date. 4. Click “Pay and Confirm Order | System should reject numeric characters in “Name on Card” and display: “Please enter a valid name.” | System accepted invalid name and completed the order successfully | High | High | https://drive.google.com/file/d/1w01S1727Q7r5FH13xETEXNIue7AYMaix/view?usp=drive_link
2 | Open | Rahma Sayed | CP07 | 1. Go to Checkout → Payment page. 2. Enter valid name. 3. Enter 10-digit card number. 4. Fill valid CVC and expiry date. 5. Click “Pay and Confirm Order.” | System should reject incomplete card numbers and display: “Please enter a valid Card Number.” | System accepted invalid card number and placed the order successfully. | High | High | https://drive.google.com/file/d/1R3sfEdSXgSiP_Ket9Klwj5kUHRf6Mc9k/view?usp=drive_link
3 | Open | Rahma Sayed | CP08 | 1. Go to Checkout → Payment page. 2. Enter valid name and card number. 3. Enter invalid CVC (letters or not 3 digits). 4. Click “Pay and Confirm Order.” | System should display: “Please enter a valid CVC.” | System accepted invalid CVC and placed the order successfully. | High | High | https://drive.google.com/file/d/1E7JeH1JI70QbU0oRME3DBQFui8XKqUpk/view?usp=drive_link
4 | Open | Rahma Sayed | CP09 | 1. Go to Checkout → Payment page. 2. Enter valid name, card number, and CVC. 3. Enter expired date (e.g., 09/2012). 4. Click “Pay and Confirm Order.” | System should reject expired or invalid date and show: “Invalid or expired date.” | System accepted expired date and confirmed the order. | High | Medium | https://drive.google.com/file/d/14dxWWzHRed1nxtqRF_QM9r5rMopXjfhs/view?usp=drive_link

## Contact Us Form
Bug # | Status | Raised By | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot (Use link from drive) | Video Recording (Use link from drive)
BUG-CU-001 | Open | Mahfouz Sherif | TC-CU-04 | 1. Go to “Contact Us” page 2. Enter Name: “12345” 3. Fill valid data in all other fields 4. Click “Submit” | Error message “Invalid name” or form not submitted | Form accepted numeric name and displayed success message | Medium | Medium | link
BUG-CU-002 | Open | Mahfouz Sherif | TC-CU-05 | 1. Go to “Contact Us” page 2. Enter Name: “@@@###” 3. Fill valid data in all other fields 4. Click “Submit” | Error message “Invalid name” or form not submitted | Form accepted special character name and displayed success message | Medium | Medium | link
BUG-CU-003 | Open | Mahfouz Sherif | TC-CU-06 | 1. Go to “Contact Us” page 2. Enter invalid Email: “mahfouz@mail” 3. Fill valid data in other fields 4. Click “Submit” | Error message “Invalid email address” | Form accepted invalid email and displayed success message | High | High | link
BUG-CU-004 | Open | Mahfouz Sherif | TC-CU-10 | 1. Go to “Contact Us” page 2. Leave Subject and Message blank 3. Fill valid data in other fields 4. Click “Submit” | Error message “Subject and Message required” | Form submitted successfully without validation | High | High | link